## List
| Type | Description | Assigned to | Assigned By | Date Entered | Status | Modified | ETA | Due
4 | Bug | Fix pull to refresh | Wil | Wil | 2021-11-06 | Open
| Task | Create settings page | Wil | Wil | 2021-11-06 | Resolved
| Task | Create better list of oddities :) | Wil | Wil | 2021-11-06 | Open
| Task | Create home screen | Wil | Wil | 2021-11-06 | Resolved
| Task | Add bias towards trends in price change | Wil | Wil | 2021-11-07 | Resolved
| Task | Create wizard secrets experience | Wil | Wil | 2021-11-06 | Resolved
| Bug | Chart bars sometimes deviate massively from correct placement | Wil | Wil | 2021-11-06 | Resolved
| Bug | Ending game/restarting game should purge all data correctly | Wil | Wil | 2021-11-06 | Resolved
| Bug | Don't show empty state when any commodities display iin the "Owned" view | Wil | Wil | 2021-11-06 | Resolved
| Bug | Make button size taller | Wil | Wil | 2021-11-06 | Resolved
| Task | Move State to speedcontrols and make button | Wil | Wil | 2021-11-06 | Resolved
| Bug | Increase hit box size for top row buttons | Wil | Wil | 2021-11-06 | Resolved
| Task | Create notification system | Wil | Wil | 2021-11-06 | Resolved
| Bug | Purchase isn't currectly adjusting for fee | Wil | Wil | 2021-11-06 | Resolved
| Task | Create opening flash screen | Wil | Wil | 2021-11-06 | Resolved
4 | Task | Add 25x speed and fix staging version | Wil | Wil | 2021-11-06 | Closed
| Bug | Add "available funds" to details page | Wil | Wil | 2021-11-06 | Closed
| Bug | Remove "Previous price" from history | Wil | Wil | 2021-11-06 | Closed
Total | [6 empty] | 0

## Legend
Open | 1
In Progress | 2
Resolved | 3
Closed | 4
Blocked | 5
Removed